## Gantt Chart
Task ID | Task | Owner | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | Dependencies | Milestone | Status
T1 | Team formation, roles, group rules, skills audits | Whole team | [8 empty] | — | M_A: Team & roles agreed | Complete
T2 | Topic selection + first client outreach email | Shilu Chuke | [8 empty] | T1 |  | Complete
T3 | First client meeting | Shilu Chuke | [8 empty] | T2 | M_B: First client meeting | Complete
T4 | A1 — Introduction + PACT Analysis | Shilu Chuke | [8 empty] | T3 |  | Complete
T5 | 3D scene technical scaffold (Three.js proof of concept) | Namshu Hang Zhyedi Magar | [8 empty] | T1 |  | Complete
T6 | A1 — Requirements document | Shilu Chuke | [8 empty] | T3 |  | Complete
T7 | Wireframes — login screen + in-game HUD | Swikriti Bashyal | [8 empty] | T4 |  | Complete
T8 | Checkpoint data structure + 3-zone navigation | Namshu Hang Zhyedi Magar | [8 empty] | T5 |  | Complete
T9 | Initial Project Plan / Gantt chart drafted | Shilu Chuke | [8 empty] | T1 |  | Complete
T10 | A1 — diagrams (use case, flowchart, architecture) | Swikriti Bashyal | [8 empty] | T6 | M_C: A1 design docs complete | Complete
T11 | Scoring engine — points awarded / penalty applied | Sparas Shrestha | [8 empty] | T8 |  | Complete
T12 | Quiz UI + first 3 checkpoints' content | Namshu Hang Zhyedi Magar | [8 empty] | T8 |  | Complete
T13 | Second client meeting — scope feedback | Shilu Chuke | [8 empty] | T3 | M_D: Scope confirmed | Complete
T14 | Login / account system + per-worker stat tracking | Sparas Shrestha | [8 empty] | T11 |  | Complete
T15 | Remaining 3 checkpoints + load-handling method logic | Namshu Hang Zhyedi Magar | [8 empty] | T12 |  | Complete
T16 | Marketing strategy draft (A6) | Swikriti Bashyal | [8 empty] | — |  | Complete
T17 | Admin Command Center + CSV export | Sparas Shrestha | [8 empty] | T14 |  | Complete
T18 | Dynamic events — streak bonus / stand-down drill | Namshu Hang Zhyedi Magar | [8 empty] | T15 | M_E: Feature-complete build | Complete
T19 | Website mockups + branding (A6) | Swikriti Bashyal | [8 empty] | T16 |  | Complete
T20 | Presentation plan + responsibility chart (A7) | Shilu Chuke | [8 empty] | T18 |  | Complete
T21 | Bug fixing from playtesting | Sparas Shrestha, Namshu Hang Zhyedi Magar | [8 empty] | T17,T18 |  | Complete
T22 | Presentation slide deck (A7) | Swikriti Bashyal | [8 empty] | T20 |  | Complete
T23 | HUD polish + backup demo video recorded | Namshu Hang Zhyedi Magar | [8 empty] | T21 |  | Complete
T24 | Full team rehearsal | Whole team | [8 empty] | T22,T23 | M_F: Rehearsal complete | Complete
T25 | Final QA pass + documentation review | Sparas Shrestha, Shilu Chuke | [8 empty] | T24 |  | Complete
T26 | Final submission — ZIP assembled + checklist review | Shilu Chuke | [8 empty] | all | M_G: A1 submitted | Complete
Legend: | green = task week |  | orange = milestone week

## Milestones
Ref | Milestone | Week | Gate | Status
M_A | Team & roles agreed | 1 | Roles allocated from skills audits; group rules agreed. | Complete
M_B | First client meeting | 2 | Client brief received for the manual-handling training concept. | Complete
M_C | A1 design docs complete | 4 | Introduction, Requirements, PACT, diagrams and system requirement analysis finished. | Complete
M_D | Scope confirmed | 5 | Second client meeting; scope adjustments agreed and incorporated. | Complete
M_E | Feature-complete build | 6 | All checkpoints, scoring, login, admin dashboard and dynamic events working. | Complete
M_F | Rehearsal complete | 8 | Full 20-minute run-through timed against the presentation plan. | Complete
M_G | A1 submitted | 8 | All seven sub-folders complete; ZIP assembled and checked. | Complete

## Notes
Lift Right — Initial Project Plan (Gantt Chart)
Eight-week plan aligned to the team's weekly meeting minutes (A4): Week 1 is team formation, Week 8 is final rehearsal and Assignment 1 submission. All eight weeks are recorded as complete against the minutes; there is no forecast/unstarted work remaining within this assignment's scope.